## Sheet1
Date | Task
2025-02-05 | Data collection and processing
2025-02-06 | Data collection and processing
2025-02-07 | Data collection and processing
2025-02-08 | Data collection and processing
2025-02-09 | Data collection and processing
2025-02-10 | Data collection and processing
2025-02-11 | Data collection and processing
2025-02-12 | Data collection and processing
2025-02-13 | Data collection and processing
2025-02-14 | Static 3DCNN Feature extraction + Traditional classifier
2025-02-15 | Static 3DCNN Feature extraction + Traditional classifier
2025-02-16 | Static 3DCNN Feature extraction + Traditional classifier
2025-02-17 | Static 3DCNN Feature extraction + Traditional classifier
2025-02-18 | Static 3DCNN Feature extraction + Traditional classifier
2025-02-19 | END-END 3D SLOWFAST CNN
2025-02-20 | END-END 3D SLOWFAST CNN
2025-02-21 | END-END 3D SLOWFAST CNN
2025-02-22 | END-END 3D SLOWFAST CNN
2025-02-23 | END-END 3D SLOWFAST CNN
2025-02-24 | END-END 3D SLOWFAST CNN
2025-02-25 | END-END 3D SLOWFAST CNN
2025-02-26 | WRITEUP
2025-02-27 | WRITEUP
2025-02-28 | INTERIM DEADLINE
2025-03-01 | END-END 3D SLOWFAST CNN
2025-03-02 | END-END 3D SLOWFAST CNN
2025-03-03 | END-END 3D SLOWFAST CNN | < - Still on SLOWFAST
2025-03-04 | TRANSFORMER MODEL
2025-03-05 | TRANSFORMER MODEL
2025-03-06 | TRANSFORMER MODEL
2025-03-07 | TRANSFORMER MODEL
2025-03-08 | TRANSFORMER MODEL
2025-03-09 | TRANSFORMER MODEL
2025-03-10 | TRANSFORMER MODEL
2025-03-11 | CNN - RNN ARCHETECTURE
2025-03-12 | CNN - RNN ARCHETECTURE
2025-03-13 | CNN - RNN ARCHETECTURE
2025-03-14 | CNN - RNN ARCHETECTURE
2025-03-15 | CNN - RNN ARCHETECTURE
2025-03-16 | CAPTION GENERATION
2025-03-17 | CAPTION GENERATION
2025-03-18 | CAPTION GENERATION
2025-03-19 | CAPTION GENERATION
2025-03-20 | CAPTION GENERATION
2025-03-21 | CAPTION GENERATION
2025-03-22 | CAPTION GENERATION
2025-03-23 | CAPTION GENERATION
2025-03-24 | CAPTION GENERATION
2025-03-25 | CAPTION GENERATION
2025-03-26 | CAPTION GENERATION
2025-03-27 | CAPTION GENERATION
2025-03-28 | CAPTION GENERATION
2025-03-29 | CAPTION GENERATION
2025-03-30 | CAPTION GENERATION
2025-03-31 | CAPTION GENERATION
2025-04-01 | CAPTION GENERATION
2025-04-02 | FINAL WRITEUP
2025-04-03 | FINAL WRITEUP
2025-04-04 | FINAL WRITEUP
2025-04-05 | FINAL WRITEUP
2025-04-06 | FINAL WRITEUP
2025-04-07 | FINAL WRITEUP
2025-04-08 | FINAL WRITEUP
2025-04-09 | FINAL WRITEUP
2025-04-10 | FINAL WRITEUP
2025-04-11 | FINAL WRITEUP
2025-04-12 | FINAL WRITEUP
2025-04-13 | FINAL WRITEUP
2025-04-14 | FINAL WRITEUP
2025-04-15 | FINAL WRITEUP
2025-04-16 | BUFFER/SPILLOVER
2025-04-17 | BUFFER/SPILLOVER
2025-04-18 | BUFFER/SPILLOVER
2025-04-19 | BUFFER/SPILLOVER
2025-04-20 | BUFFER/SPILLOVER
2025-04-21 | BUFFER/SPILLOVER
2025-04-22 | BUFFER/SPILLOVER
2025-04-23 | BUFFER/SPILLOVER
2025-04-24 | BUFFER/SPILLOVER
2025-04-25 | BUFFER/SPILLOVER
2025-04-26 | BUFFER/SPILLOVER
2025-04-27 | BUFFER/SPILLOVER
2025-04-28 | BUFFER/SPILLOVER
2025-04-29 | BUFFER/SPILLOVER
2025-04-30 | FINAL DEADLINE